TheArabAmericanUniversity

FACULTY OF Engineering and Information Technology

Engineering Project Management (11071514)

Project Name:

E-learning platform for High school students

Prepared By: Hassan Breik 201711446 Ahmad Amarneh 201811737 Feras Zayed 201620196

Instructor

Eng Mohammad Tuffaha

Introduction

ــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــ

Just as we heard the proverb that says from the womb of suffering generates hope, also new start-ups are likewise, an idea which is a solution to a real problem, solving a problem for many people, saving time and effort for everyone, and communicating information in an easier way. Our project is an electronic platform for Tawjihi students that contains rich resources to educate and teach students, ensure their understanding of materials and distinction, and obtain the best results, especially in light of the spread of Coronavirus, which makes it difficult for students to move during the existence of a ban in the country in general or some areas in particular ... For our project, we put many from the options to be the sponsor, let us ultimately only filter and select Engineer Ahmad as our sponsor for sponsoring many similar projects before and with his great experience and the capital that he owns. To make a good final product that is suitable for our dear students.

Table of Contents

Introduction.......................................................................................................... 2

Table of Contents....................................................................................................3

Chapter One: Project Pre-Initiation and Initiation

1.1    Overview

1.2	Buisness Case

1.3	Project’s Stakeholder Register

1.4     Organizational Chart

1.5	Management strategy

Chapter Two: project Planning

2.1    Overview

2.2	Project Charter

2.3	The Project Kick-off Meeting

2.4     Collecting Requirements

2.4     Project Scope Statement

2.5     WBS

2.6     WBS Dictionary

2.7     Project Schedule

2.8     Project Budget

2.9     List of prioritized risks

2.10   Milestone Report

Chapter Three: Project Execution

3.1	Overview

3.2	Performance/ Progress Report

3.4     Milestone Report Update

Chapter Four: Project Monitoring andControlling

4.1. Overview

4.2  Control Changes

4.3  Change Request

Chapter Five: Project Closing

5.1 Overview

5.2 Lessons-learned Report

Chapter Six: Conclusion

Chapter One

Project Pre-Initiation and Initiation

1.1 Overview

In the period of continuous school closures and the inability to obtain assistance and complete education for students with the presence of the virus Covid-19, especially high school students, due to its importance as a stage in the life of a learner, we will, through our project, establish an electronic and interactive learning platform for students to be able to obtain all the necessary resources and needs to be able to overcome their Ministerial exams are as required and with excellence.

Even without the presence of Corona, if we are able to pass this stage in peace and goodness, the project can continue to work on the same approach, because its way of providing videos explanations of the lessons in the best way and obtaining the information directly in an easy way

# 1.2 the scope, time, and cost constraints for the project

# - Scope:

# Providing recorded lessons for each subject according to the semester, unit and lesson in an orderly and easy manner, in addition to weekly group classes for any question, and enabling the student to hold an online session with a teacher in any subject from our side in exchange for a payment.

# - Time:

# The lessons will be prepared and filmed within two months, and at the same time the platform will be develop in two months, in a simple estimate, it will be done within two to three months.

# - Cost:

# The project will cost about (400,000 shekels) to be completed, with the calculation of the employees' salary for the first two months, the price of educational materials, and the development of the platform.

The Palestinian Ministry of Education owns an electronic platform, but the platform in our project will be easier for the student to obtain his goal and access to information. We will present the project, God willing, when it is completed to the official authorities, and we hope that the ministry will be the sponsor of the project. There is another sponsor as we mentioned in the initiation Ahmad Jaradat.

# 1.3 Business case

- Introduction/ Background We seek through the platform to help students and advancement them to get high rates, by providing all the necessary resources to obtain the information through videos, and linking them with teachers of the same specialization and the same subject who are interested in it.

2.0 Business Objective The goals of our platform include providing high school students with what they need to understand the materials without having to leave the house or waste time searching for information. The project will be characterized by the ability to take short exams online and get the result at the same moment.

3.0 Current Situation and Problem/Opportunity Statement The Ministry of Education and Higher Education has a platform similar to us, which contains some resources for learning, of course! We will be distinguished by the content we provide to students, including new explanations and methods, but we need to support the Ministry of Education so that our website becomes official so that the teachers agree to work with us and the students can trust what we offer.

4.0 Critical Assumption and Constraints The platform must be in contact with the server used by the Ministry of Education in order to be able to obtain information about students and teachers. That we can teach the professor how to do the training on our site and make an appointment with students to open a video call to create a class. The greater reliance on students to spread the word that the site is excellent for them to study and facilitate them a lot. Finally, the lessons and the videos are shot sequentially and quickly and by ensuring that the best explanations are obtained so that we can quickly launch the project to the public.

5.0 Analysis of Option and Recommendation - Only to submit tests. Creating a simple website is limited to allowing students to submit tests for the subjects they specify or the subject completely. - Posting recorded video lists. The site is divided according to the specializations of the branches, and students can only listen to the lessons recorded. - Creating a platform complete with tests, videos, and the ability of the student and teacher to establish a connection and make an interactive meeting on the Internet.

6.0 Schedule Estimate I think that the project will be completed within six months, but there is some flexibility in the schedule. We also assume that the new system will have a useful life of at least three years.

7.0 Potential Risks The project carries several risks. The foremost risk is a lack of interest in our platform by the student and teacher. User input are crucial for populating information into this system are realizing the potential benefits from using the system. There are some technical risks in choosing the type of software used to search the system, check security, process payments. The main risk that not to gain the trust of the target people.

8.0 Exhibits Exhibit A: Financial Analysis

# 1.4 The Project Stakeholders

# Stakeholder Register for E-learning platform

| Name | Position | Internal/External | Project Role | Contact Information |
| --- | --- | --- | --- | --- |
| Ahmad Jaradat | CEO | Internal | Sponsor | Ahmad@learn-pal.com |
| Hossam jalbosh | PMO Director | Internal | Project manager | Hosam@learn-pal.com |
| Amr abutamam | Team member | Internal | Team member | amr@learn-pal.com |
| Carlos Stath. | Business Analyst | external | Advisor | Carlos@learn-pal.com |
| Osama Raddad | PR Director | Internal | Advisor | osama@learn-pal.com |
| Bahaa AL Haj | Worker | Internal | Team member | Baha@leanr-pal.com |

# 1.5 Project Organizational Chart

# 1.6

# Management strategy

| Name | Level of Interest | Level of Influence | Potential Management Strategies |
| --- | --- | --- | --- |
| Ahmad Jaradat. | High | High | Ahmad like to stay on top of key projects and make money because he is a business man. Have a lot of short, face-to-face meetings and focus on achieving the financial benefits of the project. It’s the best of what out project need. |
| Amr abutamam | High | low | Amr has the very great experience that any team member of his organization needs in order to work properly with the team, we should encourage him to join with us. |
| Osama Raddad | Low | High | Osama has the character that is completely necessary for a relationship man, but he is not convinced to work with us. |

Chapter Two

Project Planning

# 2.1 Overview

Planning is the thing that interests us most in project management and its implementation mechanism. There are many important steps that we will include in our plan, such as building an online website in conjunction with the start of recording explanations for teachers and then launching and testing the site, ending with building a mobile application, and then expanding to other basic classes, all of this. As you will see, we will take it into account during the day in the planning step.

2.2 The Project Charter

Project Title: 	E-learning Platform

Project Start Date:	2-3-2022			Projected Finish Date: 3-9-2022

Budget Information:

The platform has allocated 450,000 Shekel for this project. The majority of costs for this project will be internal labor. An initial estimate provides a total of 45 hours per week.

Project Manager:  Ahmad Jaradat, 00970594131483, Ahmad@learn-pal.com

Project Objectives:

Help High school student by providing all the necessary resources to obtain the information through videos, and linking them with teachers of the same specialization and the same subject who are interested in it.

Main Project Success Criteria:

The project should pay for itself within one year of completion.

Approach:

- Developing a plan to create a new method that contributes to the delivery of the necessary knowledge to the student through the platform.

- In case the sponsor is the ministry, we will use special servers for the platform other than the ministry's servers for development and speed purposes.

- Making a plan so that we expand from the most important majors and gradually until we reach all majors in high school, then we continue with the plan to expand to the rest of the classes

- Developing a test system, so that students can make sure of their understanding of the subjects by conducting real online tests and obtaining the result.

- Developing the networking system so that the student can book an appointment with a teacher of any subject in any major can.

2.3 The Project Kick-off Meeting’

. Kick-off Meeting

15/3/2022

Project Name: E-learning platform for high school

Meeting Objective: Get the project off to a great start by introducing key stakeholders, reviewing project goals, and discussing future plans

Agenda:

- Introductions of attendees

- Background of project

- Review of project-related documents (i.e., business case, project charter)

- Discussion of project organizational structure

- Discussion of project scope, time, and cost goals

- Discussion of other important topics

- List of action items from meeting

| Action Item | Assigned To | Due Date |
| --- | --- | --- |
| The importance of team cooperation & ethics | Team members | 26-3-2022 |
| Project progress review | Sponsor, senior manager | 3/4/2022 |
| Meet their all needs | PM with IT department | 25/4/2022 |

Date and time of next meeting: 26/3/2022 at 11:00 AM.

# 2.4 Requirements Matrix for E-learning platform

Prepared by:	Hossam Jalbosh		 Date:   6/8/2021

| Requirement No. | Name | Category | Source | Status |
| --- | --- | --- | --- | --- |
| 1 | Security issues | Software | Web solutions | Done |
| 2 | Make mobile app | Software | Project charter and development | In Progress |
| 3 | Expand for other classes | All Steps was made before | Feature Planning to expand | Hold |

# 2.5 project scope statement

Scope Statement (Version A)

Project Title: Project management E-learning platform Date: 18/3/2022 Prepared by: Hossam Jalbosh

Project Justification: Ahmad Jaradat CEO of E-learning platform , requested this project to assist the company in meeting its strategic goals. The new E-learning platform site will increase visibility of the teaching teacher’s expertise to current and potential students how can use internet methods and use our site. our Site will also help reduce private lessons costs and improve teaching by providing standard tools, techniques, exams templates, and all new features to all students. The budget for the project is 375,000 shiekl . An additional 45,000 shiekl per year will be Required for teaching operations after the project is completed. Estimated benefits are 1,000,000 shiekl each year. It is important to focus on the system paying for itself within half one year of its completion..

Product Characteristics and Requirements: - Search feature: The intranet site must include a search feature for users to search by topic, key words, etc. - The platform site must be available 24 hours a day, 7 days a week, with one hour per week for system maintenance and other periodic maintenance, as appropriate. - The “Ask the teacher” feature must be user-friendly and capable of make questions and immediately acknowledging that the question has been received. The feature must also be capable of forwarding the question to the appropriate teacher (as maintained in the system’s database) and capable of providing the status of questions that are answered. The system must also allow for payment for asks, if appropriate. - Requests for explain lesson: The platform will include a section for users to ask someone from the Project Office (PO) at our platform at each specific to lesson appropriate for them. The PO manager must first approve the request and negotiate payments, if appropriate. - Templates and tools: The platform will allow authorized users to download files they can use to create documents and to help them use platform tools. These files will be in Microsoft Word, Excel, Access, Project, or in HTML or PDF format, as appropriate.

Summary of Project Deliverables Project management-related deliverables: business case, charter, team contract, scope statement, WBS, schedule, cost baseline, status reports, final project presentation, final project report, lessons-learned report, and any other documents required to manage the project. Product-related deliverables: 1. Survey: Survey current teachers and students to help determine desired content and features for the platform. 2. Files for templates: The platform will include templates for at least 7 documents when the system is first implemented, and it will have the capacity to store up to 100 documents. The project team will decide on the initial 3 templates based on survey results. 3. Instructions for using platform tools: The platform will include information on how to use several platform tools, including the following as a minimum: ask the expert, videos, written lessons and earned ask for a lesson. Where appropriate, sample files will be provided in the platform. For example, Microsoft Project files will be available to show summarize articles. 4. Articles: The platform will include at least 10 useful articles about relevant topics in each specific. The platform will have the capacity to store at least 1,000 articles in PDF format with an average length of 10 pages each.

Project Success Criteria: Our goal is to complete this project within six months for no more than 470,000 shikel. The project sponsor, Ahmad Jaradat has emphasized the importance of the project paying for itself within half one year after the platform is complete. To meet this financial goal, the platform must have strong user inputs. We must also develop a method for capturing the benefits while the platform is being developed and tested, and after it is rolled out. If the project takes a little longer to complete or costs a little more than planned, the firm will still view it as a success if it has a good payback .

# 2.6 work breakdown structure (WBS) and WBS dictionary

Work Breakdown Structure Template for E-learning platform

Prepared by:	Hossam Jalbosh			Date:	3/4/2022

1.0 Initiating

1.2 Prepare project charter

1.3 Hold project kick-off meeting

2.0 Planning

2.1 Hold team planning meeting

2.2 Prepare scope statement

2.3 Prepare WBS

2.4 Prepare schedule and cost baseline

2.5.1 Determine task resources

2.5.2 Determine task durations

2.5.3 Create draft Gantt chart

2.6 Identify, discuss, and prioritize risks

3.0 Executing

3.1 Survey

3.2 User inputs

3.3 platform content

3.3.1 Templates and tools

3.3.2 Articles

3.3.3 Links

3.3.4 Ask the teacher

3.4 platform design

3.5 platform construction

3.6 platform testing

3.7 platform promotion

3.8 platform roll-out

3.9 Project benefits measurement

4.0 Monitoring and Controlling

4.1 Progress reports

5.0 Closing

5.1 Prepare final project report

5.2 Prepare final project presentation

5.3 Lessons learned

2.7 BS dictionary

# 2.8 E-learning platform Budget

| Project Cost Estimate |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date:5/4/2022 |  |  |  |  |  |  |
|  | # Units/Hrs. | Cost/Unit/Hr In sheikl | Subtotals | WBS Level 1 Totals | % of Total |  |
| WBS Items |  |  |  |  |  |  |
| 1. Project Management |  |  |  | 20,000 | 20% |  |
| 1.1 Project manager | 960 | 100 | 96,000 |  |  |  |
| 1.2 Project team members | 1920 | 75 | 144,000 |  |  |  |
| Contractors (10% of software development and testing) |  |  | 66,300 |  |  |  |
| 2. Hardware |  |  |  | 76,000 | 5% |  |
| 2.1 Handheld devices | 100 | 600 | 60,000 |  |  |  |
| 2.2 Servers | 4 | 4,000 | 16,000 |  |  |  |
| 3. Software |  |  |  | 614,000 | 40% |  |
| 3.1 Licensed software | 100 | 200 | 20,000 |  |  |  |
| 3.2 Software development* |  |  | 594,000 |  |  |  |
| 4. Testing (10% of total hardware and software costs) |  |  | 69,000 | 69,000 | 5% |  |
| 5. Training and Support |  |  |  | 202,400 | 13% |  |
| 5.1 Trainee cost | 100 | 500 | 50,000 |  |  |  |
| 5.2 Travel cost | 12 | 700 | 8,400 |  |  |  |
| 5.3 Project team members | 1920 | 75 | 144,000 |  |  |  |
| 6. Reserves (20% of total estimate) |  |  | 253,540 | 253,540 | 17% |  |
| Total project cost estimate |  |  |  | 1,521,240 |  |  |

# 2.8.1E-learning platform Financial Analysis

Example Payback period:

| Year | Costs | Benefits | Cum Costs | Cum Benefits |
| --- | --- | --- | --- | --- |
| 0 | 470,000 | 20,000 | 470,000 | 0 |
| 1 | 2,000,000 | 800,000 | 177,200 | 186,000 |
| 2 | 400,000 | 1,250,000 | 211,600 | 358,000 |
| 3 | 90,000 | 2,100,000 | 243,200 | 4,150,000 |

2.9 A list of prioritized risks (part of a risk register)

List of Prioritized Risks for E-learning platform

Prepared by:	Hossam Jalbosh				Date:  9/5/2022

| Ranking | Potential Risk |
| --- | --- |
| 1 | Providing an efficient search feature |
| 2 | Getting good feedback from students |
| 3 | Effectively promoting the new system for mobile app |
| 4 | Realizing the benefits of the new class expand within two year |
| 5 | Lack of inputs from teachers |
| 6 | Lack of inputs from client representatives |

2.10 Mile Stone report

| Milestone | Date | Status | Responsible | Issues/Comments |
| --- | --- | --- | --- | --- |
| Initiating |  |  |  |  |
| Identifying stakeholders | 10/3/22 | complete | Ahmad |  |
| Develop project charter | 10/3/22 | complete | Hossam |  |
| Prepare project charter | 15/3/22 | complete | Hossam |  |
| Sign project charter | 20/3/22 | complete | All |  |
| planning |  |  |  |  |
| Determine project team | 21/3/22 | Complete | Ahmad |  |
| Make team contract | 25/3/22 | Complete | Hossam |  |
| Project scope statement | 28/3/22 | complete | Hossam |  |
| Define requirements | 30/3/22 | complete | All | Both requirments |
| Project schedule | 1/4/22 | complete | Hossam saaed |  |
| Create gantt chart | 2/4/22 | complete | Hossam |  |
| Review gantt chart | 3/4/22 | complete | All |  |
| Prioritized risk | 9/5/22 | complete | Hossam |  |
| Project plan | 14/5/22 | complete | All |  |
| Develop project plan | 15/5/22 | complete | Hossam |  |
| Review project plan | 16/5/22 | complete | All team |  |
| Executing |  |  |  |  |
| Implementation | 17/5/22 | complete | Hossam |  |
| Install software on computers | 20/5/22 | complete | Carlos |  |
| Prepare the website for use | 20/5/22 | complete | Carlos |  |
| Learn the training staff on how to use devices | 22/5/22 | complete | Carlos |  |
| Test software | 24/5/22 | complete | Carlos |  |
| start students registration | 29/5/22 | complete | Carols |  |
| Monitoring and Controlling |  |  |  |  |
| status report | 1/6/22 | complete | All |  |
| Report performance | 2/6/22 | complete | Saaed, carlos |  |
| Daily meeting |  | complete | all |  |
| Control changes | 10/5/22 | complete | Carlos, Hossam saaed |  |
| Closing |  |  |  |  |
| Prepare project report | 1-6-22 | complete | Hossam |  |
| Prepare final project presentation | 2-6-22 | complete | All |  |
| Lessons learned report | 3-6-22 | complete | All |  |

Chapter Three

Project Execution

______________________________________________

3.1	Overview

Project execution involves taking the necessary actions to ensure the completion of activities in the project plan. It also includes the work required to introduce any new hardware, software and procedures in regular operations. Project products are created during project execution, and it usually takes most resources to complete this process.

3.2	Performance/ Progress Report

| Milestone | Date | Status | Responsible | Issues/Comments |
| --- | --- | --- | --- | --- |
| initiating | 8/2/2022 | completed |  | No Issues |
| Identify key stakeholders | 13/12/2021 | completed |  | No Issues |
| Write introduction | 18/12/2021 | completed | Ahmad,Feras | No Issues |
| Project charter | 7/1/2022 | completed | Ahmad,Feras,Hassan | No Issues |
| Charter sign | 7/1/2022 | completed |  | No Issues |
| Prepare team contract | 22/1/2022 | completed | Ahmad | No Issues |
| Establish wbs | 4/1/2022 | Completed | Ahmad,Feras,Hassan | No Issues |
| Develop scope statement | 16/3/2022 | completed | Feras,Hassan | No Issues |
| Project schedule | 6/4/2022 | completed | Ahmad,Feras,Hassan | No Issues |
| Cost estimate | 5/1/2022 | completed | Ahmad,Hassan | No Issues |
| System design | 24/3/2022 | completed | Ahmad,Feras,Hassan | No Issues |
| System development | 13/6/2022 | completed | Ahmad,Feras,Hassan | No Issues |
| System testing | 8/6/2022 | completed |  | No Issues |
| Present final project | 10/6/2022 | completed | Hassan | No Issues |
| Project completed | 20/6/2022 | completed | Hassan | No Issues |

3.4     Milestone Report Update

In our E-learning platform for High school students we put the most important activity and define if it completed or not and who is responsible for it, we added the best choices for the system and gave it a view of experience

Chapter Four

Project Monitoring andControlling

______________________________________________________________________

4.1. Overview

Monitoring and control is the process of measuring progress toward project goals, monitoring deviation from the plan, and taking corrective actions to match progress with the plan. Monitoring and control take place throughout the life of the project. It also includes nine of the ten areas of knowledge for project management.

4.2  Control Changes

Change control is of particular importance when the project is part of a larger programme or portfolio because the consequential effects of unmanaged change may be far-reaching within the planned change environment and to business-as-usual activities.

The project professional implements the following steps to control change:

- Log change request in a change register (or log).

- Initial evaluation where the change is reviewed.

- Detailed evaluation where the impact on baseline success criteria, benefits, scope, quality, time, resources, costs, risks, stakeholder engagement or any other criteria important to achieving the business case are considered.

- A recommendation is made to the sponsor and/or wider governance board to approve, reject or defer the change.

- The plan is updated is a change is approved.

- Implementation where the necessary actions are taken and monitored.

It is important to differentiate change control from the wider discipline of change management. Change control is a subset of overall change management and it is useful to not mix up the language. Change management is a structured approach to move an organisation from a current state to a future desired state.

4.3  Change Request

Change requests may arise as a result of issues that occur from the management of work or external sources. Issues that result in changes to scope or any other part of the baseline plan are progressed through change control.

Any success criteria that need to be changed at any time in the project life cycle are subject to approval through change control. Formal change control is required when tolerances are breached

Change control is of particular importance when the project is part of a larger programme or portfolio because the consequential effects of unmanaged change may be far-reaching within the planned change environment and to business-as-usual activities.

Chapter Five

Project Closing

_____________________________________________________________________

5.1 Overview

Finalize all activities across all of the process groups to formally close and there is example for closing the project below.

5.2 Lessons-learned Report

Project Name: E-learning platform Project Sponsor: Ahmad jaradat Project Manager: Hossam Jalbosh Project Dates: 1/6/2022 – 19/6/2022

- Did the project meet scope, time, and cost goals? The Project have reached his scope in make videos, features and resources to help student learn in internet, we were not successful in Time because the Project take more time than we have planned, the cost have been exactly as we planned and execute, at all we have make good job in meet the three goals. - What was the success criteria listed in the project scope statement? Reach our goal to make the Platform Besides all the difficulties we have gone through. - Reflect on whether or not you met the project success criteria. Project is completed in scope goal, Project is completed in budget, Project deliverables are fit for purpose, good quality and the project haven’t attached because of his good security. - In terms of managing the project, what were the main lessons your team learned? In the specializations divisions for high school students, the valley made parts in an orderly and beautiful way in order for the student to access and understand them. - Describe one example of what went right on this project. When starting filming lectures, teachers and students had an effective and excellent role in their learning on the platform, starting to shoot videos for teachers and taking private lessons for students through teachers, this was one of the best things that happened. - Describe one example of what went wrong on this project. The design and construction of the site requires a longer time than we expected, and the lack of a strong Internet we have made it difficult for us to do the task of uploading videos on the Internet and taking more time than necessary, and this was the worst thing we experienced. - What will you do differently on the next project based on your experience working on this project? Building and developing the site took more time than necessary, next time we will talk with experienced people to determine a better time and increase the time during the planning process.

Chapter Six

Conclusion

__________________________________________________________________________________

We think that our project is really useful and it help a large group of people, some of its most important benefits will give a better education system for the future and there is going to be updated on it by time

References:

- Project Microsoft office

- Click Chart diagram

- Minister of education Palestine