# The Arab American University

# Faculty of Engineering and Information Technology

# Engineering Project Management (11071514)

# iStudent E-learning Platform

Prepared by:

Mohammad Abu Malash - 201911801

Moath Abu Malash – 201912230

Hassan Braik – 201711446

Basil Salahat – 201811775

Instructor

Eng Mohammad Tuffaha

June 2023 © Arab American University – Palestine

Contents

Introduction	4

1.	Project Pre-Initiation and Initiation	6

1.1.	Overview	6

1.2.	The scope, time, and cost constraints for the project	6

1.3.	Business case	7

1.4.	Project’s Stakeholders Register	13

1.5.	Project Organizational Chart	14

1.6.	Management Strategy	14

2.	Project Planning	17

2.1.	Overview	17

2.2.	Project Charter	17

2.3.	The Project Kick-off Meeting	21

2.4.	Collecting Requirements	22

2.5.	Project Scope Statement	22

2.6.	Work Breakdown Structure (WBS)	25

2.7.	WBS Dictionary	27

2.8.	Project Schedule	27

2.9.	Project Budget/ Financial Analysis (Payback Analysis, NPV, RoI)	27

2.10.	List of prioritized risks	30

2.11.	Milestone Report	31

3.	Project Execution	35

3.1.	Overview	35

3.2	Performance/ Progress Report	35

3.2.	Milestone Report Update	36

4.	Project Monitoring and Controlling	40

4.1.	Overview	40

4.2.	Control Changes	40

4.3.	Change Request	41

5.	Project Closing	43

5.1	Overview	43

5.2	Lessons-learned Report	43

6.	Conclusion	47

References:	48

List of Tables

Table 1Stakeholder Register for E-learning Platform	14

Table 2 Management Strategy	15

# Introduction

Similar to the proverb that states "hope is born from the womb of suffering," new start-ups embody the same essence. They are born from ideas that provide solutions to real problems, addressing the needs of many people, and making information more accessible, saving time and effort for everyone involved. Our venture focuses on creating an online platform specifically designed for Tawjihi students. It offers a wide array of resources aimed at educating and training students, ensuring their comprehension of subjects and topics, and enabling them to achieve the best possible results. This is particularly important in light of the ongoing Coronavirus pandemic, which has imposed travel bans and restrictions, making it challenging for students to move freely within the country, or even in certain regions.

Chapter One

Project Pre-Initiation

&

Initiation

# Project Pre-Initiation and Initiation

## Overview

During the period of prolonged school closures caused by the Covid-19 virus, students, especially high school students, have faced significant challenges in accessing educational assistance and completing their studies. Recognizing the critical importance of this stage in a learner's life, our project aims to establish an interactive and electronic learning platform. This platform will provide students with all the necessary resources and support they need to excel in their Ministerial exams.

Even without the presence of the Covid-19 pandemic, our project has the potential to continue its impact. By offering comprehensive video explanations of lessons and providing information in a direct and easily accessible manner, our platform addresses the fundamental needs of students. Thus, even under normal circumstances, the project's approach remains relevant and valuable in ensuring students' successful progression and understanding of their educational materials.

## The scope, time, and cost constraints for the project

- Scope:

Our project aims to offer a well-structured and user-friendly learning experience by providing recorded lessons for each subject, organized according to the semester, unit, and lesson. Students can easily access these lessons and study at their own pace. Additionally, we will conduct weekly group classes where students can ask questions and engage in collaborative learning. To further support students' individual needs, we will offer the option to schedule online sessions with our qualified teachers for additional guidance in any subject, with a corresponding fee. This comprehensive approach ensures that students have access to high-quality educational resources and personalized assistance to enhance their understanding and excel academically.

- Time:

The completion of our project involves a two-month timeline for class preparation and an additional two months for platform construction. In summary, the entire project is expected to be finished within a timeframe of approximately four months.

- Cost:

The estimated total cost of the project, encompassing the acquisition of instructional materials, platform development, and staff salaries for the initial two-month period, is approximately 400,000 shekels. It's worth noting that while there is an existing electronic platform owned by the Palestinian Ministry of Education, our proposed platform aims to simplify the student's journey and provide easier access to necessary information, thereby enhancing their ability to achieve their objectives.

## Business case

Business Case for iStudent E-learning Platform

Date: 25 May 2023

Prepared by: Basil Salahat

- Introduction/ Background Our platform is dedicated to supporting students and enabling them to achieve high academic performance. We provide a comprehensive range of resources, including video content, to facilitate easy access to information. Moreover, we connect students with specialized teachers who have a genuine interest and expertise in the subject matter. By offering these valuable resources and connections, our platform aims to empower students and propel them towards attaining excellent academic results. Our ultimate goal is to facilitate student success and foster their academic advancement.

2.0 Business Objective Our platform's objectives revolve around catering to the needs of high school students by offering them a convenient way to comprehend their study materials without the need to leave their homes or spend time searching for information elsewhere. The project emphasizes efficiency by providing quick access to relevant resources. Moreover, our platform enables students to take short online exams and receive immediate results, enhancing their learning experience and providing valuable feedback in real-time. By combining accessibility, convenience, and instant feedback, our platform aims to streamline the learning process for high school students and optimize their educational outcomes.

3.0 Current Situation and Problem/Opportunity Statement While acknowledging the presence of a similar platform offered by the Ministry of Education and Higher Education, we aim to distinguish ourselves through the unique content we provide to students. Our platform will offer fresh explanations and innovative teaching methods, supplementing the existing resources. However, in order to gain the trust of both teachers and students, it is crucial to secure the support of the Ministry of Education. By establishing an official partnership with the ministry, we can collaborate with teachers and gain their endorsement, ensuring that students can have confidence in the quality and reliability of our platform. We recognize the importance of working in harmony with the education authorities to create a trusted and effective learning environment for the students we serve.

4.0 Critical Assumption and Constraints In order to access student and instructor data, our platform needs to establish communication with the Ministry of Education's server. This connectivity allows us to facilitate video conferences with students, enabling us to create interactive classrooms and train professors on effectively utilizing our website for educational purposes. We also recognize the significance of leveraging student testimonials to promote our platform's effectiveness in studying and its overall benefits. To expedite the project's launch, we prioritize the efficient production of courses and videos while ensuring the highest quality explanations are captured. This approach enables us to promptly introduce the project to the public, ensuring a comprehensive and impactful learning experience for students.

5.0 Analysis of Option and Recommendation - Our initial focus will be on developing a streamlined website that allows students to submit tests for specific subjects or the entire curriculum. The website's primary functionality will be limited to facilitating exam submissions. - Additionally, we will provide a comprehensive collection of recorded videos on the platform. These videos will be categorized based on subject specialties, allowing students to easily access and listen to recorded lectures and course materials. - As part of our long-term plans, we aim to develop an advanced platform that goes beyond basic functionalities. This comprehensive platform will include interactive quizzes, a wide range of educational videos, and the capability for students and instructors to connect and engage in interactive online meetings. This integrated approach will foster an interactive and immersive learning experience for students, providing them with the tools necessary to excel in their studies.

6.0 Preliminary Project Requirements - User Registration and Authentication: - Users should be able to create accounts and register on the platform. - The platform should provide authentication mechanisms to ensure secure access. - User Profiles: - Users should have personal profiles where they can manage their information, including name, contact details, and preferences. - Course Management: - The platform should support the creation and management of courses. - Course creators should be able to upload course content, such as videos, documents, and quizzes. - Courses should be categorized and searchable for easy navigation. - The platform should support multiple types of courses, such as video-based, text-based, or interactive courses. - Enrollment and Payment: - Users should be able to enroll in courses and make payments securely. - The platform should offer various payment options, such as credit/debit cards, PayPal, or other payment gateways. - Progress Tracking and Reporting: - The platform should track and display the progress of learners in their enrolled courses. - Learners should have access to their course completion certificates or badges. - Discussion and Collaboration: - The platform should provide a discussion forum or chat feature to facilitate learner interaction and collaboration. - Users should be able to ask questions, participate in discussions, and receive guidance from instructors or peers. - Notifications and Reminders: - The platform should send notifications and reminders to learners about course updates, upcoming assignments, and deadlines. - Analytics and Insights: - The platform should provide analytics and insights to course creators and administrators, allowing them to track learner engagement, course popularity, and other relevant metrics. - Mobile-Friendly Interface: - The platform should have a responsive design that adapts to different screen sizes, ensuring a user-friendly experience on mobile devices. - Admin Dashboard: - The platform should have an administrative dashboard to manage user accounts, courses, payments, and overall platform functionality.

7.0 Budget Estimate and Financial Analysis - Software development: This includes the cost of hiring developers or development team, either in-house or outsourced, to build the platform. - Platform infrastructure: Costs associated with servers, hosting, cloud services, and database management. - Third-party integrations: If you plan to integrate with payment gateways, analytics tools, or other external services, there may be associated costs. - If you are developing your own course content, consider the cost of subject matter experts, instructional designers, multimedia creators, and content editors. - Alternatively, if you plan to license or purchase existing courses, factor in the costs of acquiring the content. - User interface (UI) and user experience (UX) design costs, including graphic design, wireframing, and prototyping. - Marketing efforts to attract learners to the platform, including digital marketing campaigns, content marketing, social media promotion, and advertising costs. - Ongoing maintenance and support costs, such as bug fixes, feature updates, server maintenance, and technical support for users. - Determine how the e-learning platform will generate revenue. This may include course enrollment fees, subscription fees, advertising revenue, or a combination of various monetization models. - Calculate the return on investment (ROI) and determine the break-even point based on projected revenues and expenses. This helps assess the financial viability and potential profitability of the platform.

8.0 Schedule Estimate The estimated timeline for project completion is approximately four months, although there is some flexibility in the schedule to accommodate any unforeseen circumstances or adjustments. Furthermore, we assume that the newly developed system will have a minimum useful life of three years. This assumption ensures that the system will continue to serve its intended purpose effectively and provide long-term benefits to the students and users of the platform.

9.0 Potential Risks The project entails various risks that need to be addressed. The primary risk involves a potential lack of interest from both students and teachers in adopting and utilizing our platform. User engagement and input play a critical role in populating the system with relevant information and unlocking the full potential benefits of the platform. There are also technical risks associated with selecting the appropriate software for system search capabilities, ensuring robust security measures, and implementing seamless payment processing. These technical aspects require careful consideration and mitigation to minimize potential issues and vulnerabilities. However, the most significant risk lies in gaining the trust of our target audience. Building trust among students, teachers, and other stakeholders is essential for the success of our project. We must establish credibility, reliability, and demonstrate the value and effectiveness of our platform to overcome this risk and gain the confidence of our intended users. Implementing transparency, maintaining open communication, and consistently delivering on our promises will be key in building trust and fostering widespread adoption of our platform.

10.0 Exhibits Exhibit A: Financial Analysis.

## Project’s Stakeholders Register

Stakeholder Register for iStudent E-learning Platform

Prepared by: Moath Abu Malash

Date: 23/5/2023

| Name | Position | Internal/ External | Project Role | Contact Information |
| --- | --- | --- | --- | --- |
| Ministry | Sup owner | external | Sponsor | Ministry@gmail.com |
| Mohammad Abu Malash | CEO | Internal | Owner | Mohammad@learn-pal.com |
| Moath Abu Malash | Manager | Internal | Project manager | Moath @learn-pal.com |
| Basil Salahat | Leader | Internal | Team Coordinator | Basil@learn-pal.com |
| Hassan Braik | Procurement Manager | external | Advisor | Carlos@learn-pal.com |
| Lojain Ahmad | Team member | Internal | Team Member | Lojain @learn-pal.com |
| Sarah Salahat | Team member | Internal | Team Member | sarah@learn-pal.com |

Table 1Stakeholder Register for E-learning Platform

## Project Organizational Chart

Organizational Chart for iStudent E-learning Platform
 Prepared by: Mohammad Abu Malash
Date:26 May 2023

Figure 1 Project Organizational Chart

## Management Strategy

Stakeholder Management Strategy for iStudent E-learning Platform

Prepared by: Basil Salahat

Date: 26 / 5 / 2023

| Name | Level of Interest | Level of Influence | Potential Management Strategies |
| --- | --- | --- | --- |
| Mohammad Abu Malash | High | High | Mohammad Abu Malash is the CEO and the owner of the project he has a good look at the market and human sources with a lot of experience to stay on top of key projects as a businessman. Have a lot of short, face-to-face meetings and focus on achieving the financial benefits of the project. |
| Moath Abu Malash | Medium | low | Moath Abu Malash has a lot of great experience that any team member of his organization needs to work properly with the team. |
| Basil Salahat | High | Medium | Basil Salahat has the character that is completely necessary for a relationship man. |

Table 2 Management Strategy

Chapter Two

Project Planning

# Project Planning

## Overview

Planning is a crucial aspect of project management that greatly interests us. We recognize the significance of a well-structured plan and its implementation mechanism. Our project plan encompasses several essential steps, starting with the development of an online website while simultaneously recording explanations provided by teachers. Subsequently, we will proceed with the launch and testing of the website. As a progressive step, we intend to build a mobile application to further enhance accessibility. Additionally, we plan to expand our services to cover other fundamental subjects. These considerations will be carefully incorporated into our planning process to ensure their seamless execution throughout the project timeline.

## Project Charter

Project Title: iStudent E-learning Platform

Project Start Date: 20/5/2023			Projected Finish Date: 26/6/2023

Budget Information:

The platform has allocated 450,000 Shekel for this project. The majority of costs for this project will be internal labor. An initial estimate provides a total of 45 hours per week.

Project Manager:

Moath Abu Malash, 0568335980, m.abumalash@student.auup.edu

Project Objectives:

Our primary objective is to provide comprehensive support to high school students by offering them a wide range of valuable resources. To facilitate their learning process, we will curate informative videos that cover various subjects. Moreover, we aim to establish connections between students and passionate teachers who specialize in the same subject matter. By fostering these connections, students can benefit from direct interactions, clarifications, and personalized guidance. Our goal is to create an environment where students have easy access to educational materials and a supportive network of teachers dedicated to their academic success.

Main Project Success Criteria:

- Financial self-sufficiency achieved within one-year post-completion.

- Stakeholder and beneficiary satisfaction and approval.

- Alignment with shareholders' and markets' requirements.

- Successful attainment of projected profits.

Approach:

Our project involves several key components aimed at revolutionizing the delivery of essential knowledge to students through our platform. To ensure a successful implementation, we will develop a comprehensive plan encompassing the following aspects:

- Innovative Knowledge Delivery Method: We are committed to creating a novel approach that enhances the learning experience for students. Our plan entails developing a unique method within our platform, leveraging engaging content, interactive features, and intuitive interfaces to facilitate effective knowledge transfer.

- Dedicated Servers for Ministry Sponsorship: If the Ministry becomes our sponsor, we will prioritize the utilization of dedicated servers exclusively for our platform. This strategic decision aims to ensure optimal performance, scalability, and speed, thereby guaranteeing a seamless learning experience for students.

- Gradual Expansion to Major Subjects: Our expansion plan is designed to prioritize the most important majors initially and gradually extend our coverage to encompass all high school subjects. This approach allows us to focus on providing quality resources and targeted support to students in key subjects before widening our scope to include other academic disciplines.

- Comprehensive Testing System: To assess students' understanding and progress, we will implement a robust online testing system. This feature empowers students to evaluate their knowledge through real-time online exams and receive immediate results. The testing system aims to enhance self-assessment and provide valuable insights for further improvement.

- Enhanced Networking System: We recognize the importance of fostering connections between students and teachers across different subjects and majors. Our networking system will facilitate seamless appointment bookings, enabling students to schedule personalized sessions with teachers of their choice. This feature promotes individualized guidance and support tailored to students’ unique academic needs.

Additionally, we will continue to refine our plan and incorporate any necessary components to ensure the success and scalability of our project. Our goal is to establish a comprehensive educational ecosystem that empowers students, nurtures their academic growth, and fosters a passion for lifelong learning.

Roles and Responsibilities

| Role | Name | Organization/ Position | Contact Information |
| --- | --- | --- | --- |
| Project manager | Moath Abu Malash | PM | 05683303801 |
| Sponsor | Mohammad Abu Malash | Owner | Mohammad@gmail.com |
| Team member | Hassan Briek | Supplier | 0598754991 |
| Team member | Basil Salahat | Leader | Basil@gmail.com |
| Team member | Lojain Ahmad | Developer | Lojain@gmail.com |
| Team member | Sara Salahat | Developer | Lian@gmail.com |
| Adviser | Dr. Mohammad Tuffaha | Professor | Mohammad.Tuffaha@student.aaup.edu |

Sign-off:

Dr. Mohammad Tuffaha

Mohammad Jamal

Moath Jamal

Hassan Briek

Basil Salahat

Sara Salahat

Lojain Ahmad

## The Project Kick-off Meeting

Kick-off Meeting

Date: 27/5/2023

Project Name: iStudent E-learning Platform

Meeting Objective:

Get the project off to a great start by introducing key stakeholders, reviewing project goals, and discussing future plans.

Agenda:

- Introductions of attendees

- Background of project

- Review of project-related documents (i.e., business case, project charter)

- Discussion of project organizational structure

- Discussion of project scope, time, and cost goals

- Discussion of other important topics

- List of action items from meeting

| Action Item | Assigned To | Due Date |
| --- | --- | --- |
| Define project scope | Hassan, Mohammad, Basil | 3/6/2023 |
| Discuss project background | Moath | 27/5/2023 |
| Define the goals of the project | Basil | 30/5/2023 |
| Define rules and responsibilities | Team members | 26/5/2023 |
| Milestone Report | Moath | 10/6/2023 |

Date and time of next meeting: 10/6/2023 at 11:00 AM.

## Collecting Requirements

| Requirement No. | Name | Category | Source | Status |
| --- | --- | --- | --- | --- |
| 1 | Security issues | Software | Web solutions | Done |
| 2 | Make mobile app | Software | Project charter and development | In Progress |
| 3 | Expand for other classes | All Steps was made before | Feature Planning to expand | Hold |

## Project Scope Statement

Scope Statement (Version 1)

Project Title: iStudent E-learning Platform Date: 2/6/2023 Prepared by: Hassan Braik

Project Justification: Mohammad Jamal, CEO of iStudent E-learning platform, has initiated this project to align with the company's strategic objectives. The objective is to create an innovative E-learning platform that enhances the visibility of teachers' expertise, utilizing internet-based methods and our dedicated site. This platform aims to reduce the costs of private lessons, while simultaneously improving teaching quality by providing standardized tools, techniques, exam templates, and introducing new features for all students. The allocated budget for the project is 375,000 shiekl. Additionally, an annual investment of 45,000 shiekl will be required for ongoing teaching operations after the project's completion. The estimated annual benefits are projected to be 1,000,000 shiekl. A key focus for the project is achieving self-sustainability within six months of its completion.

Product Characteristics and Requirements: - Search Functionality: The intranet site should incorporate a user-friendly search feature that enables users to search for specific topics or keywords within the platform. - 24/7 Platform Availability: The platform site must be accessible 24 hours a day, 7 days a week, with a designated one-hour weekly maintenance window for system updates and periodic maintenance activities. - "Ask the Teacher" Feature: The "Ask the Teacher" feature should provide a seamless user experience by promptly acknowledging received questions. It should also route the questions to the appropriate teacher based on the system's database and offer status updates on answered questions. The system should also facilitate payment options if required. - Lesson Explanation Requests: The platform will include a dedicated section where users can request explanations for specific lessons. These requests will be reviewed and approved by the Project Office (PO) manager, who will also handle negotiations regarding any necessary payments. - Templates and Tools: Authorized users will have the ability to download various file formats, including Microsoft Word, Excel, Access, Project, HTML, or PDF, as needed. These files will serve as templates and tools to assist users in document creation and utilizing platform features effectively.

Summary of Project Deliverables Product-related deliverables: - Survey: Conduct a comprehensive survey among current teachers and students to gather insights on their preferences and requirements for content and platform features. - Template Files: Develop and provide a collection of templates for various documents. Initially, at least seven templates will be included upon the platform's launch, with the capability to accommodate up to 100 templates. The selection of the initial three templates will be based on the survey results. - Platform Tools Instructions: Create user-friendly instructions for utilizing various platform tools, including "Ask the Expert," video resources, written lessons, and requesting specialized lessons. Where applicable, sample files, such as Microsoft Project files, will be made available to demonstrate tool functionality and enhance user understanding. - Relevant Articles: Curate a comprehensive library of valuable articles, with a minimum of 10 articles per specific topic. The platform will have the capacity to store over 1,000 articles in PDF format, with an average length of 10 pages each. These articles will cover a wide range of relevant subjects, providing valuable resources for users.

Project Success Criteria: Our objective is to successfully deliver this project within a six-month timeframe while keeping the budget under 470,000 shikel. Mohammad Jamal, our project sponsor, has emphasized the significance of the platform becoming financially self-sustainable within six months after its completion. Achieving this financial goal relies on active user engagement and feedback. Additionally, we need to devise a methodology to track and measure the benefits of the platform during its development, testing, and post-rollout stages. Even if there are slight delays or cost variations in the project, the firm will consider it a triumph as long as it demonstrates a favorable payback.

## Work Breakdown Structure (WBS)

Work Breakdown Structure Template for iStudent E-learning platform

Date: 10/6/2023	    	                Prepared by: Mohammad Jamal

- Initiating

  - Select project manager.

  - Prepare project charter

  - Hold project kick-off meeting

  - Stake holder register

  - Determine the required resource.

    - User requirements.

    - System requirements

- Planning

  - Hold team planning meeting

  - Prepare team contract

  - Prepare scope statement

  - Prepare WBS

  - Prepare schedule and cost baseline

    - Determine task resources

    - Determine task durations

    - Create draft Gantt chart

  - Identify, discuss, and prioritize risks

- Executing

  - Survey

  - User inputs

  - platform content

    - Templates and tools

    - Articles

    - Links

    - Ask the teacher

  - Platform design

  - Platform construction

  - Platform testing

  - Platform promotion

  - Platform roll-out

  - Project benefits measurement

- Monitoring and Controlling

  - Progress reports

  - Project reports.

    - Change requests.

    - Updates

- Closing

  - Prepare final project report

  - Prepare final project presentation

  - Lessons learned

## WBS Dictionary

WBS that conveys detailed info about each component. It’s one of the five pillars that support the scope management in your project

These five components will give you the scope baseline for your project. Without a project scope baseline, you can’t measure performance effectively, which puts your project in danger of going off schedule and beyond budget.

the details of the tasks, activities, and deliverables of the work breakdown structure are located. The content includes whatever milestones are related, the project scope and in some instances dates, resources, cost and quantity.

Work Breakdown Structure Template for Project Name: iStudent E-learning Platform.

## Project Schedule

In the form of a Gantt chart with all dependencies and resources entered and Network Diagram.

THIS PART NEED MS PROJECT THAT WE DID NOT TAKE

## Project Budget/ Financial Analysis (Payback Analysis, NPV, RoI)

| Prepared by: Mohammad Jamal | Date: | 6/6/2023 |
| --- | --- | --- |

| Project Cost Estimate |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date: 5/4/2022 |  |  |  |  |  |  |
|  | # Units/Hrs. | Cost/Unit/Hr In sheikl | Subtotals | WBS Level 1 Totals | % of Total |  |
| WBS Items |  |  |  |  |  |  |
| 1. Project Management |  |  |  | 20,000 | 20% |  |
| 1.1 Project manager | 960 | 100 | 96,000 |  |  |  |
| 1.2 Project team members | 1920 | 75 | 144,000 |  |  |  |
| Contractors (10% of software development and testing) |  |  | 66,300 |  |  |  |
| 2. Hardware |  |  |  | 76,000 | 5% |  |
| 2.1 Handheld devices | 100 | 600 | 60,000 |  |  |  |
| 2.2 Servers | 4 | 4,000 | 16,000 |  |  |  |
| 3. Software |  |  |  | 614,000 | 40% |  |
| 3.1 Licensed software | 100 | 200 | 20,000 |  |  |  |
| 3.2 Software development* |  |  | 594,000 |  |  |  |
| 4. Testing (10% of total hardware and software costs) |  |  | 69,000 | 69,000 | 5% |  |
| 5. Training and Support |  |  |  | 202,400 | 13% |  |
| 5.1 Trainee cost | 100 | 500 | 50,000 |  |  |  |
| 5.2 Travel cost | 12 | 700 | 8,400 |  |  |  |
| 5.3 Project team members | 1920 | 75 | 144,000 |  |  |  |
| 6. Reserves (20% of total estimate) |  |  | 253,540 | 253,540 | 17% |  |
| Total project cost estimate |  |  |  | 1,521,240 |  |  |

2.8.1E-learning platform Financial Analysis

Example Payback period:

| Year | Costs | Benefits | Cum Costs | Cum Benefits |
| --- | --- | --- | --- | --- |
| 0 | 470,000 | 20,000 | 470,000 | 0 |
| 1 | 2,000,000 | 800,000 | 177,200 | 186,000 |
| 2 | 400,000 | 1,250,000 | 211,600 | 358,000 |
| 3 | 90,000 | 2,100,000 | 243,200 | 4,150,000 |

## List of prioritized risks

List of Prioritized Risks for iStudent E-learning platform

Prepared by:	Lojain Ahmad				Date: 5/6/2023

| Ranking | Potential Risk |
| --- | --- |
| 1 | Providing an efficient search feature |
| 2 | Getting good feedback from students |
| 3 | Effectively promoting the new system for mobile app |
| 4 | Realizing the benefits of the new class expand within two years |
| 5 | Lack of inputs from teachers |
| 6 | Lack of inputs from client representatives |

## Milestone Report

# Milestone Report for iStudent E-learning Platform

Prepared by:	Sara Salahat				Date:9/6/2023

| Milestone | Date | Status | Responsible | Issues/Comments |
| --- | --- | --- | --- | --- |
| Initiating |  |  |  |  |
| Identifying stakeholders | 20/5/23 | Completed | Moath |  |
| Prepare project charter | 23/5/23 | Completed | Mohammad |  |
| Sign project charter | 24/5/23 | Completed | Mohmmad |  |
| Project kick-off meeting held | 27/5/23 | Completed |  | Went well |
| Planning |  |  |  |  |
| Team contract signed | 27/5/23 | Completed | Moath |  |
| Project scope statement | 30/5/23 | Completed | Hassan |  |
| WBS | 31/5/23 | Completed | Sara |  |
| List of prioritized risks | 5/6/23 | Completed | Hassan |  |
| schedule and cost baseline | 6/6/23 | Completed |  |  |
| Create gantt chart | 8/6/23 | Completed | Moath |  |
| Review gantt chart | 9/6/23 | Completed | All |  |
| Executing |  |  |  |  |
| Survey | 20/6/23 |  | Hassan |  |
| platform design | 27/6/23 |  | Team |  |
| Implementation | 5/8/23 |  | Team |  |
| Test software | 10/8/23 |  | Mohammad and the team |  |
| Promotion | 16/8/23 |  |  |  |
| Release | 17/8/23 |  |  |  |
| Monitoring and controlling |  |  |  |  |
| Status Report | 20/8/23 |  | All |  |
| Performance Report | 22/8/23 |  | Moath |  |
| Closing |  |  |  |  |
| Prepare project report | 24/8/23 |  | Moath |  |
| Prepare final project presentation | 25/8/23 |  | All |  |
| Lessons learned report | 26/8/23 |  | All |  |

Chapter Three

Project Execution

# Project Execution

# Overview

Project execution involves taking the necessary actions to ensure the completion of activities in the project plan. It also includes the work required to introduce any new hardware, software and procedures in regular operations. Project products are created during project execution, and it usually takes most resources to complete this process.

## 3.2	Performance/ Progress Report

# Performance /Progress Report

Project Name: iStudent E-learning Platform Team Member Name: Hassan Briek Date: Reporting Period:

- Work completed this reporting period: - Developed user registration and login functionality. - Created the course management module. - Implemented the payment integration for course enrollment. - Designed the user interface for the homepage.

- Work to complete next reporting period: - Develop the course content management system. - Integrate the discussion forum feature. - Implement the progress tracking functionality. - Enhance the user interface for mobile devices.

What’s going well and why: - The team has successfully completed the initial phase of the project, including user registration, login, and basic course management. The progress is on track because we established clear milestones and allocated sufficient resources for each task. - The payment integration for course enrollment is working smoothly. We collaborated effectively with the payment gateway provider, which facilitated a seamless integration process.

What’s not going well and why: - The development of the course content management system has faced some delays due to unforeseen technical challenges. This has slowed down progress in this area. - The UI/UX for mobile devices needs improvement, as it has not been fully optimized for smaller screens. This has caused some usability issues for mobile users.

Suggestions/Issues: - Address the technical challenges in developing the course content management system promptly and allocate additional resources if necessary to expedite the process. - Conduct thorough testing on various mobile devices to identify and fix any UI/UX issues for optimal user experience.

#### Project changes: None at the moment.

# Milestone Report Update

| Milestone | Date | Status | Responsible | Issues/Comments |
| --- | --- | --- | --- | --- |
| Initiating | 20/5/2023 | Completed | Moath | No Issues |
| Identify key stakeholders | 21/5/2023 | Completed | Moath | No Issues |
| Write introduction | 23/5/2023 | Completed | Hassan and Moath | No Issues |
| Project charter | 30/5/2023 | Completed | Basil | No Issues |
| Charter sign | 1/6/2023 | Completed | Basil | No Issues |
| Prepare team contract | 13/6/2023 | Completed | Mohammad | No Issues |
| Establish wbs | 26/6/2023 | Completed | Basil | No Issues |
| Develop scope statement | 1/7/2023 | Completed | Basil & hassan | No issues |
| Project schedule | 9/7/2023 | Completed | Mohammad | No Issues |
| Cost estimate | 21/7/2023 | Completed | Mohammad | No Issues |
| System design | 28/7/2023 | Completed | Basil & moath & hassan | No issues |
| System development | 8/8/2023 | Completed | Mohammad & moath | No issues |
| System testing | 20/8/2023 | Completed | Basil | No Issues |
| Present final project | 25/8/2023 | Completed | Hassan | No Issues |
| Project completed | 26/8/2023 | Completed | Hassan | No Issues |

Chapter Four

Project Monitoring and Controlling

# Project Monitoring and Controlling

## Overview

Monitoring and control is the way we keep track of how a project is going. We measure how well we're doing compared to our goals and check if we're following the plan. If we notice any problems or mistakes, we take steps to fix them and get back on track. Monitoring and control happen from the beginning to the end of a project. It covers most of the important things we need to know about managing a project.

## Control Changes

Change control is really important, especially when a project is part of a bigger program or group of projects. If changes aren't managed properly, they can have a big impact on the planned changes and the regular activities of the business. It's crucial to keep everything in check to avoid any negative consequences.

The project professional follows these steps to control change:

- Record the change request in a change register or log.

- Review the change in an initial evaluation.

- Conduct a detailed evaluation, considering how the change will impact the project's goals, benefits, scope, quality, time, resources, costs, risks, stakeholder engagement, and other important criteria for achieving the project's objectives.

- Make a recommendation to the sponsor or governance board to approve, reject, or postpone the change.

- Update the plan if the change is approved.

- Implement the change by taking necessary actions and monitoring the process.

It's important to understand that change control is different from change management as a whole. Change control is a part of the broader discipline of change management. It's helpful to use clear language and not confuse the two. Change management is a structured approach to guide an organization from its current state to a desired future state.

## Change Request

Change requests can come up due to problems that arise during the project or from external sources. If there are any issues that require changes to the project's scope or other parts of the original plan, they are handled through change control.

Approval through change control is necessary for any changes to the success criteria of the project, regardless of the project's stage. Formal change control becomes necessary when the set tolerances are exceeded.

Change control is especially crucial when the project is part of a larger program or portfolio. Unmanaged changes can have significant consequences not only within the planned changes but also for the ongoing business activities. It's important to manage changes properly to avoid any far-reaching effects.

Chapter Five

Project Closing

# Project Closing

## 5.1	Overview

To formally close the project, complete all activities across all process groups. Here's an example of the project closure process:

- Complete all remaining project deliverables and ensure they meet the required quality standards.

- Conduct a final project review to assess whether all project objectives have been achieved.

- Document any lessons learned throughout the project's duration, capturing both successes and challenges faced during the process.

- Perform a thorough project documentation review to ensure all records are complete and accurate.

- Obtain formal approval and sign-off from stakeholders to acknowledge the successful completion of the project.

- Release and communicate the final project deliverables to relevant stakeholders and end-users.

- Ensure all project resources are appropriately released and reallocated to other initiatives as necessary.

- Conduct a post-project evaluation to measure the project's overall success against initial goals and expectations.

- Organize a project closure meeting or session to celebrate the team's accomplishments and recognize their efforts.

- Archive all project-related documents and materials for future reference and audit purposes.

## 5.2	Lessons-learned Report

# Lessons Learned Report

Prepared by: Basil Salahat Date: 1/7/2023 Project Name: iStudent E-learning Platform Project Sponsor: Mohammad Abu Malash Project Manager: Moath Abu Malash Project Dates: 20/5/2023 - 26/6/2023 Final Budget: 1,521,240

- Did the project meet scope, time, and cost goals? The project aimed to create videos, features, and resources to facilitate student learning on the internet. While we successfully achieved the scope of the project, we faced challenges in meeting the timeline as it took longer than initially planned. However, we were able to manage the costs exactly as planned and executed. Overall, we did a commendable job in accomplishing the three main goals of the project. - What was the success criteria listed in the project scope statement? Despite all the difficulties we have faced, we have successfully reached our goal of creating the platform. - Reflect on whether or not you met the project success criteria. The project has been successfully completed within the defined scope, staying within the allocated budget. The project deliverables meet the intended purpose and exhibit good quality. Additionally, the project has been well-protected due to its robust security measures, avoiding any potential breaches or vulnerabilities. - In terms of managing the project, what were the main lessons your team learned? The valley has organized and presented the different specialization divisions for high school students in a clear and visually appealing manner, making it easy for students to access and comprehend the information. - Describe one example of what went right on this project. The process of filming lectures had a significant and positive impact on the learning experience of both teachers and students on the platform. Teachers actively participated in creating video lectures, while students benefited from personalized lessons conducted by teachers. This development has been regarded as one of the most beneficial and valuable aspects of the platform. - Describe one example of what went wrong on this project. The design and construction of the website took more time than originally anticipated. Additionally, the lack of a reliable internet connection posed challenges in uploading videos to the internet, causing further delays. This proved to be the most significant setback we encountered throughout the project. - What will you do differently on the next project based on your experience working on this project? The construction and development of the website took longer than expected. In the future, we plan to consult experienced individuals to accurately determine the required time and allocate sufficient time during the planning phase. This will help us streamline the process and avoid unnecessary delays.

Chapter Six

Conclusion

# Conclusion

We strongly believe that our project is highly beneficial and serves a large community of individuals. Among its significant advantages is the contribution towards improving the education system for future generations. Moreover, we are committed to regularly updating and enhancing the project over time to ensure its continuous relevance and effectiveness.

## References:

Minister of education Palestine